## How to use
RecruiterOS — Outreach Engine: Master Build Plan
WHAT THIS IS
A systematized, prioritized checklist to get the whole outreach model firing: acquire data → enrich it → attach hiring signals → auto-generate grounded content → reach out across email, LinkedIn (connect / profile view / voice note / message) and voicemail drops — then orchestrate it as one working loop.
HOW TO USE THE TABS
• 'Master To-Do' — the full prioritized list. Filter the Status column to see what's left to build vs already built.
• 'Channel Playbook' — best-practice cadence & guardrails per channel (rapport-first).
• 'Keys & Accounts' — the env keys/accounts to set, with status.
STATUS LEGEND
✅ Built — already in the codebase (verify it still fires). 🔧 Wire-up — pieces exist, need connecting. 🏗 Build — net-new work. ⚙ Config — a key/account to set.
PRIORITY LEGEND
P0 = do now (unblocks the core loop). P1 = next. P2 = foundation/scale, do when forced.
RECOMMENDED SEQUENCE
1) Phase 0 keys → 2) verify Phases 1–7 each fire end-to-end (most are already built) → 3) build the two real gaps: the email→voicemail auto-trigger (7.3) and the unified multi-channel sequence (8.1) → 4) run the end-to-end smoke test (8.5) → 5) deliverability guardrails (Phase 9) → 6) infra foundations (Phase 10) only when something forces it.
THE TWO REAL FUNCTIONAL GAPS (everything else is verify or config)
• 7.3 email-sent → voicemail auto-trigger (Track A) — highest payoff, smallest build.
• 8.1 unified multi-channel sequence wiring across all channels.
Larger optional tracks: B = own email stack, C = KV→SQL migration.
GROUND RULE (non-negotiable)
Every persuasive move is anchored to a REAL observed fact and a TRUE claim. Never fabricate people, stats, or outcomes. Symptom (job posting) vs cause (business problem). Human-in-loop on the top slice before any send.

## Master To-Do
RecruiterOS — Outreach Engine Build Checklist
Legend: ✅ Built · 🔧 Wire-up · 🏗 Build · ⚙ Config ¦ Priority: P0 = now · P1 = next · P2 = later. Filter the Status column to see what's left.
ID | Priority | Workstream | Task | What it does / why | Status | Depends on | Tools / Keys | Done when
PHASE 0 — Foundations: accounts, keys, env (do first — unblocks everything)
0.1 | P0 | Setup | Create integration/.env from .env.example | Secrets file the app reads (not committed). | ⚙ Config / Account | — | (file) | integration/.env exists on your machine.
0.2 | P0 | Setup | Set Anthropic key | Powers JD parse, fit-scoring, all content generation. | ⚙ Config / Account | 0.1 | ANTHROPIC_API_KEY | A test LLM call returns text.
0.3 | P0 | Setup | Set RapidAPI people-search key(s) | Discovery at scale (cheapest fast path). | ⚙ Config / Account | 0.1 | RAPIDAPI_PEOPLE_SEARCH_* | A search query returns prospects.
0.4 | P0 | Setup | Set Apify token + direct-dial actor id | Finds person direct lines (~$0.03 each). | ⚙ Config / Account | 0.1 | APIFY_TOKEN, APIFY_DIRECT_DIAL_ACTOR | Enrich-phone returns a number.
0.5 | P0 | Setup | Set Telnyx key (voice/AMD + a number) | Voicemail drops + line-type confirm. | ⚙ Config / Account | 0.1 | TELNYX_API_KEY | A test voice drop hits your phone.
0.6 | P0 | Setup | Connect Unipile + your LinkedIn account | LI connect / profile-view / voice-note / message / reply-read. | ⚙ Config / Account | 0.1 | UNIPILE_* keys | LinkedIn account shows connected in Accounts.
0.7 | P0 | Setup | Confirm dial cost cap | Hard guardrail — person-direct only. | ✅ Built | 0.5 | RECRUITEROS_MAX_DIAL_USD=0.03 | Cap enforced; never raise without explicit say-so.
0.8 | P0 | Decision | Pick email sending model for now (Instantly) vs own stack later | Sets Phase 9/10 scope. | ⚙ Config / Account | — | — | Decision recorded (see Phase 10 Track B).
PHASE 1 — Data acquisition / discovery
1.1 | P0 | Discovery | Verify JD → ICP parser (titles, seniority, geo, industries, target cos, must/nice/dq) | Turns a JD into a structured ideal-customer profile. | ✅ Built – verify | 0.2 | Anthropic (Haiku) | Uploading a JD returns a structured ICP.
1.2 | P0 | Discovery | Verify ICP → search-query generator (LinkedIn URLs + Google X-ray) | Feeds the existing import engine. | ✅ Built – verify | 1.1 | Anthropic | One ICP yields dozens of queries.
1.3 | P0 | Discovery | Verify discovery orchestrator (fan-out → import → dedupe by LI URL → cap) | One JD → ~1,000 ranked prospects. | ✅ Built – verify | 1.2, 0.3 | RapidAPI / scraper | One JD produces ~1,000 deduped prospects.
1.4 | P1 | Discovery | Set default discovery source + fallback (RapidAPI fast vs free scraper $0/slow) | Sets cost & ToS risk per run. | 🔧 Wire-up | 0.3 | — | Default chosen; low-volume falls back to scraper.
1.5 | P0 | Discovery | Verify Data Warehouse import (licensed CSV / ZoomInfo) into persisted people store | Bulk licensed data → searchable, promotable. | ✅ Built | — | (CSV) | A CSV import is searchable and promotable.
1.6 | P1 | Discovery | Harden cross-source identity resolution (LinkedIn URL = primary key) | Same person from 2 sources must merge, not duplicate. | 🔧 Wire-up | 1.5 | — | Duplicates across sources merge cleanly.
PHASE 2 — Enrichment (contact data, cheapest-first)
2.1 | P0 | Enrichment | Verify cheapest-first email/phone waterfall (enrichProspect) | Lowest-cost verified contact per person. | ✅ Built | — | enrichment keys | Name+company yields verified email/phone at lowest cost.
2.2 | P0 | Enrichment | Test Apify direct-dial + Telnyx line-type confirm (landline/VoIP only; mobiles filtered) | The phone half of the voice loop. | ✅ Built – verify | 0.4, 0.5 | Apify, Telnyx | Enrich-phone returns a tagged landline; logs $0.03.
2.3 | P0 | Enrichment | Enforce on-demand enrichment (only the slice you'll contact) | Avoids the classic cost trap (~$2/job vs ~$16). | 🔧 Wire-up | 2.1 | — | Enrichment is selection-driven, not all-1,000-upfront.
2.4 | P1 | Enrichment | Email verification before trusting marketplace data | Marketplace rows are unverified. | 🔧 Wire-up | 2.1 | verify API | Risky emails flagged before any send.
2.5 | P1 | Enrichment | Verify free email/phone backfill on campaign-add (warehouse) | Auto-fills contacts from the store at no cost. | ✅ Built | 1.5 | — | Adding to a campaign auto-fills contacts.
PHASE 3 — Hiring signals (the trigger layer)
3.1 | P0 | Signals | Inventory signal sources + set keys (TheirStack postings, PDL, people graph) | ~90% already built — confirm wired. | ✅ Built – verify | 0.1 | TheirStack/PDL keys | All signal sources enumerated and keyed.
3.2 | P0 | Signals | Verify hiring-signal ingestion (job postings → company hiring intent) | Postings → scored signal on a company/lead. | ✅ Built – verify | 3.1 | — | A new posting creates a scored signal.
3.3 | P1 | Signals | Map signal → outreach trigger (symptom=posting, cause=biz problem) | Fresh signal auto-enqueues a touch. | 🔧 Wire-up | 3.2, 4.x | — | A fresh signal can enqueue a first touch.
3.4 | P1 | Signals | Signal freshness / recency scoring + dedupe | Stale signals must decay, not re-fire. | 🔧 Wire-up | 3.2 | — | Old signals decay; no duplicate firing.
3.5 | P1 | Signals | Verify BD Companies signal-driven status + functional tags | Company status reflects live signals. | ✅ Built – verify | 3.2 | — | Company status/tags track signals.
PHASE 4 — Content automation (personalized, grounded copy)
4.1 | P0 | Content | Verify recruiting rapport-rung drafter (linkedin/personalize) — recognize→pitch ladder | One grounded touch per channel from a prospect+JD. | ✅ Built – verify | 0.2 | Anthropic | A prospect+JD yields a grounded first touch.
4.2 | P0 | Content | Commit + wire BD persona messaging (lib/bd/personaMessaging.ts) — full multi-channel package | Currently untracked in git — 12-field JSON pack per exec lead. | 🔧 Wire-up | 0.2 | Anthropic | Exec lead → 12-field pack lands in approval queue.
4.3 | P0 | Content | Enforce ethics guardrail (every claim anchored to a REAL fact; never fabricate people/stats) | Non-negotiable house rule. | ✅ Built | — | — | Generator refuses unfounded claims.
4.4 | P1 | Content | Emit channel-specific variants (email / LI msg / LI voice-note script / VM script) from one pack | One lead → all four channel drafts. | 🔧 Wire-up | 4.1, 4.2 | — | One lead emits all 4 channel drafts.
4.5 | P1 | Content | Verify A/B variant generation (campaigns/abtest) | Test subject/opener variants. | ✅ Built | — | — | Two variants generate and track.
4.6 | P0 | Content | Verify approval queue (human-in-loop on top slice before send) | Keep a human on the top slice. | 🔧 Wire-up | 4.1 | — | Drafts queue for approve/edit before send.
PHASE 5 — Channel: Email
5.1 | P0 | Email | Verify email send transport (currently Instantly) | Baseline send path. | ✅ Built – verify | 0.8 | Instantly key | A test email sends and logs.
5.2 | P0 | Email | Verify open/click/reply tracking + reply ingestion (response/ingest) | Closes the loop; routes replies. | ✅ Built | 5.1 | IMAP/webhook | A reply auto-routes and is recorded.
5.3 | P0 | Email | Verify per-lead cadence/sequence engine (campaigns/cadence,sequence) | Multi-step email on schedule. | ✅ Built | 5.1 | — | A multi-step sequence runs on schedule.
5.4 | P0 | Email | Verify suppression / unsubscribe / bounce handling (response/suppression) | Stops sends to opt-outs/bounces. | ✅ Built | 5.2 | — | Opt-outs and bounces stop future sends.
PHASE 6 — Channel: LinkedIn (connect / view / voice-note / message)
6.1 | P1 | LinkedIn | Verify Unipile provider + rate limiter connected | Account active within daily caps. | ✅ Built – verify | 0.6 | Unipile | LI account active and inside daily caps.
6.2 | P1 | LinkedIn | Verify connection requests (with personalized note) | Recognize, no pitch. | ✅ Built – verify | 6.1 | Unipile | A CR sends; acceptance is detected.
6.3 | P1 | LinkedIn | Verify scheduled profile views (warm signal) | Soft warm-up before connect. | 🔧 Wire-up | 6.1 | Unipile | Profile views fire within caps.
6.4 | P1 | LinkedIn | Verify post-accept messages | Continue the thread after accept. | ✅ Built – verify | 6.2 | Unipile | A message sends after acceptance.
6.5 | P1 | LinkedIn | Verify LinkedIn voice notes deliver | Human voice builds rapport. | 🔧 Wire-up | 6.1 | Unipile (confirm support) | A voice note delivers to a connection.
6.6 | P1 | LinkedIn | Verify rate limiter / daily caps / human-like pacing (rateLimiter) | Protects the account from flags. | ✅ Built | 6.1 | — | Caps enforced; no account flags.
6.7 | P1 | LinkedIn | Verify LI sequence engine interleaves with email/VM (sequenceEngine) | One multi-channel timeline. | ✅ Built – verify | 6.1, 5.3 | — | LI steps interleave in one sequence.
PHASE 7 — Channel: Voicemail drops
7.1 | P1 | Voicemail | Verify Telnyx AMD voice drop to landline/VoIP (cloned voice) | The drop machinery. | ✅ Built – verify | 0.5 | Telnyx | A drop lands on your own phone.
7.2 | P1 | Voicemail | Verify consent + timezone-window + mobile-strip gates | Only eligible landlines, in-window. | ✅ Built | 7.1 | — | Drops fire only to eligible landlines in-window.
7.3 | P0 | Voicemail | BUILD auto-trigger: email-sent → voicemail drop fires automatically (Track A) | The one genuine functional gap in the core loop. | 🏗 Build | 5.1, 7.1 | — | Sending an email auto-enqueues the VM drop.
7.4 | P1 | Voicemail | Verify LinkedIn-first voice funnel (note on accept; AMD+landline on the rest) | Recently shipped routing. | ✅ Built – verify | 6.2, 7.1 | — | Funnel routes correctly per accept state.
PHASE 8 — Orchestration: putting it together
8.1 | P0 | Orchestration | Wire unified multi-channel sequence (email + LI connect/view/voice/msg + VM) | One prospect on one timeline across all channels. | 🔧 Wire-up | 5.x,6.x,7.x | — | A prospect flows through all channels on one timeline.
8.2 | P1 | Orchestration | Channel-selection logic per lead (data completeness → channels) | No phone → skip VM, etc. | 🔧 Wire-up | 8.1 | — | Leads route only to channels they qualify for.
8.3 | P0 | Orchestration | Reply / positive-signal → auto-pause sequence + route to human | Stop nagging once they engage. | 🔧 Wire-up | 5.2 | — | A reply halts remaining steps.
8.4 | P1 | Orchestration | Daily queue worker / scheduler (cron) | Runs the day's queue unattended. | 🔧 Wire-up | 8.1 | cron | Engine processes the daily queue unattended.
8.5 | P0 | Orchestration | End-to-end smoke test (JD → discover → enrich → signal → draft → approve → send all channels) | Proves the whole model fires. | 🔧 Wire-up | all above | — | One lead completes the full loop in staging.
PHASE 9 — Deliverability & best-practice guardrails
9.1 | P1 | Deliverability | Provision sending domains + mailboxes (SPF / DKIM / DMARC) | Inbox placement foundation. | 🏗 Build | 0.8 | DNS / domains | Domains authenticated and passing.
9.2 | P1 | Deliverability | Mailbox warmup before volume | New mailboxes must ramp first. | 🏗 Build | 9.1 | Mailivery / warmup | Warmup ramps before real sends.
9.3 | P1 | Deliverability | Volume caps / throttling per mailbox + per LI account | Stay under provider limits. | 🔧 Wire-up | 9.1, 6.6 | — | Daily limits enforced across channels.
9.4 | P1 | Deliverability | Outreach tab: real warm sending-domain tracking (replace card #5 demo) | Card #5 is demo data today. | 🏗 Build | 9.1 | lib/sending (not on main) | All 6 cards show live domain/warmup health.
9.5 | P0 | Deliverability | Compliance: opt-out language, consent records, suppression honored everywhere | Legal + reputational floor. | 🔧 Wire-up | 5.4 | — | Every channel honors suppression + logs consent.
PHASE 10 — Infrastructure foundations (do when something forces it)
10.1 | P2 | Infra | KV → real SQL tables (contacts/campaigns/messages/events/voice_drops) — Track C | Foundation the spec assumes. | 🏗 Build | — | Postgres | Storage runs on SQL; JSON snapshots retired.
10.2 | P2 | Infra | Self-hosted email stack (Postal MTA / Winnr + Mailivery warmup) — Track B | Replaces Instantly with owned infra. | 🏗 Build | 0.8 | Winnr/Postal, Mailivery | Own stack sends + warms.
10.3 | P2 | Infra | Wire ledger metering (email / AI / SMS / fixed-cost accrual) | Spending dashboard still shows modeled, not metered. | 🏗 Build | — | rates.ts | Dashboard shows metered actuals.
10.4 | P2 | Infra | BD Companies real backend store (replace in-memory CSV seed) | Companies must persist across restarts. | 🏗 Build | — | Postgres/KV | Companies persist across restarts.
10.5 | P2 | Infra | Guard the file-volume logout bug on deploy | Recurring persistence issue. | 🔧 Wire-up | — | — | Deploys don't log you out.
PHASE 11 — Measurement & iteration
11.1 | P2 | Metrics | Reconcile spending projection vs actuals | Projected vs metered per recruiter. | 🔧 Wire-up | 10.3 | — | Projection and metered actuals reconcile.
11.2 | P2 | Metrics | Funnel metrics by channel (discovered→enriched→contacted→replied→meeting) | See where the funnel leaks. | 🔧 Wire-up | 8.5 | — | Dashboard shows conversion by channel.
11.3 | P2 | Metrics | Feed A/B results back into content generation | Winners inform next drafts. | 🔧 Wire-up | 4.5 | — | Winning variants influence new drafts.
11.4 | P2 | Metrics | Cost-guardrail alerts (dial cap, enrichment, LLM spend) | Catch overspend early. | 🔧 Wire-up | 0.7 | — | Overspend triggers an alert.

## Channel Playbook
Channel Playbook — rapport-first cadence & guardrails
Governing rule: every persuasive move is anchored to a REAL observed fact and a TRUE claim. Symptom (job posting) vs cause (business problem). One ask per touch. Recognize → pitch ladder. Human-in-loop on the top slice.
Channel / Move | Purpose & best practice | Cadence position | Guardrails / caps
LinkedIn profile view | Soft warm signal, no ask. Shows up in their notifications. | Day 0 (before connect) | Within daily view cap; spread out.
LinkedIn connection request (+ note) | Recognize them; reference a real observed fact. NO pitch. | Day 1 | ~15–25/day; always personalized.
Email touch 1 | Interest-coincidence open: their business problem (cause), not the posting (symptom). One question, one ask. | Day 2–3 | Warmed domain; <~50/mailbox/day.
LinkedIn voice note (post-accept) | Human voice builds rapport fast. 20–30s, grounded, friendly. | After acceptance | Connections only; confirm Unipile support.
Voicemail drop (landline/VoIP) | Cloned voice, natural, in-window. Fires automatically after email send. | Auto after email touch | Landline/VoIP only; consent + timezone; $0.03 dial cap.
Email follow-ups | Add value, don't nag. New angle each time. | Day 5, 9, 14 | Honor suppression; stop on reply.
LinkedIn message (post-accept) | Continue the thread; one question per touch. | Interleaved with email | Daily caps; human-like pacing.
Reply / positive signal | Pause ALL remaining steps; route to a human immediately. | On any reply | Opt-out → suppress everywhere.

## Keys & Accounts
Keys & Accounts Checklist
Fill integration/.env. You don't need every key at once — only the ones for the feature you're testing.
Service / Account | Env var(s) | Used for | Status
Anthropic | ANTHROPIC_API_KEY | JD parse, fit-scoring, all content generation | ⚙ Config / Account
RapidAPI (people search) | RAPIDAPI_PEOPLE_SEARCH_* | Discovery at scale (fast path) | ⚙ Config / Account
Apify | APIFY_TOKEN, APIFY_DIRECT_DIAL_ACTOR | Direct-dial phone finder (~$0.03) | ⚙ Config / Account
Telnyx | TELNYX_API_KEY | Voice/AMD drops + line-type confirm | ⚙ Config / Account
Unipile | UNIPILE_* keys | LinkedIn connect/view/voice/message/reply | ⚙ Config / Account
Dial cost cap | RECRUITEROS_MAX_DIAL_USD | Hard cap = 0.03; never raise | ✅ Built
LLM model override | RECRUITEROS_LLM_MODEL | Defaults to claude-sonnet-4-6 | ✅ Built
Instantly (current email) | (provider key) | Email send today (until own stack) | ⚙ Config / Account
TheirStack / PDL | (signal keys) | Hiring-signal sources | ⚙ Config / Account
Winnr + Mailivery (future) | (stack keys) | Own sending + warmup (Track B) | 🏗 Build